Sprint 3 Review & Sprint 4 Plan

Management Report      DRAFT - for review

# Executive Summary

Sprint Health: GREEN  -  goal substantially met.

18 of 30 items completed (60%), with 12 carried over. Beneath the raw count: of 23 items committed at sprint start, 14 shipped (61%), and the team absorbed 7 items added mid-sprint, completing 4 of them.

The headline: the Wompi switch landed. The external blocker that held Sprint 2 to a partial goal is resolved - billing now runs on the ReformAI account. Alongside it, the team stood up code review, productionized the operational health dashboard, and added Google Cloud health monitoring. Four of the six goal pillars are complete; the remaining two (Jira/GitHub integration, project-from-a-visualization) are in progress, not missed.

## Sprint 3 Outcome

| Metric | Result |
| --- | --- |
| Committed (final) | 30 |
| Completed | 18 |
| Completion rate | 60% |
| Carried over | 12 |

By initiative (completed / total):

| Initiative | Completed | Total |
| --- | --- | --- |
| Product | 6 | 12 |
| Infrastructure | 3 | 6 |
| Business Design | 4 | 6 |
| Tech Debt | 3 | 4 |
| Uncategorized | 2 | 2 |

By work type (completed / total):

| Type | Completed | Total |
| --- | --- | --- |
| Story | 14 | 23 |
| Bug | 4 | 7 |

## Goal Assessment

Jira goal: Technical hardening sprint: complete the Wompi switch to the ReformAI account, productionize the operational health dashboard, add Google Cloud health monitoring, and stand up code review + Jira/GitHub integration. User feature: create a project from a visualization.

| Goal component | Outcome |
| --- | --- |
| Complete the Wompi switch to the ReformAI account | Complete |
| Productionize the operational health dashboard | Complete |
| Add Google Cloud health monitoring | Complete |
| Stand up code review | Complete |
| Jira / GitHub integration | Partial |
| User feature: create a project from a visualization | Partial |

## Scope: Committed vs Added Mid-Sprint

Point-in-time counts hide mid-sprint additions. Pulled from the Jira sprint report:

| Bucket | Count | Completed | Carryover | Rate |
| --- | --- | --- | --- | --- |
| Committed at start | 23 | 14 | 9 | 61% |
| Added mid-sprint | 7 | 4 | 3 | 57% |
| Removed after start | 0 | - | - | - |

Note: the 3 added items that carried over are all reactive production/registration bugs (RAI-661, RAI-662, RAI-664). Late, unplanned bug work is exactly what the new Production Bugs bucket is designed to absorb in Sprint 4.

## Velocity - Completed by Size

| XS | S | M | Spike | Unsized |
| --- | --- | --- | --- | --- |
| 3 | 6 | 6 | 1 | 2 |

Sized velocity sample: 16 items (2 completed items were unsized). Against the Sprint 2 baseline (3 M), mid-size (M) throughput rose to 6. Still no L or larger completed - the second sprint running - which is the key input to Sprint 4 capacity.

## Highlights

- Wompi account switched over. The Sprint 2 external blocker is resolved; billing runs on the ReformAI account.

- Health monitoring implemented. Operational health dashboard productionized and Google Cloud monitoring added (retro flags a few gaps still to close).

- Code review stood up in GitHub, with Jira/GitHub integration in progress.

- Asset Discovery Pipeline shipped.

## Watch Items (from the retro)

- Prod regressions from hotfixes. Directly motivated the Production Bugs bucket and a per-build test-suite idea for Sprint 4.

- Operational Health still missing some things - follow-up scope.

- Service Providers' projects not showing up - now filed as a Sprint 4 bug.

- Supplier Catalog is hard to design without enough client catalogs to generalize from - blocks the design work carried into Sprint 4.

- Venezuela new-market design pulled focus from sprint initiatives.

## Retro Summary

What went well

- Wompi Account Switched Over

- Health Monitoring Implementations

- Asset Discovery Pipeline

Could be better

- Regression with Hot fixes to prod

- Operational Health is missing some things

- Today’s Service Providers Projects not showing up

- Business Design on the Supplier Catalog - without have enough clients with a catalog it is hard to design a one size fits all

- Venezuela new market design took away from Sprint Initiatives

Ideas

- Need to have standard user checks for all tabs pages

- Test suite for each new build to complete

# Sprint 4 Plan

Goal: Compiled Infrastructure Report + GCP Visualization Insight + Partner Projects UI Overhaul

Readiness Gate: READY  -  stories sized, all items assigned and epic-linked, goal set. Bugs are intentionally unsized (capacity held in the Production Bugs bucket).

## Committed Scope

24 items  -  12 carryover, 12 net-new.

| Initiative | Items |
| --- | --- |
| Product | 11 |
| Infrastructure | 8 |
| Business Design | 4 |
| Tech Debt | 1 |

By size:

| XS | S | M | L | Spike | Unsized |
| --- | --- | --- | --- | --- | --- |
| 1 | 8 | 8 | 3 | 1 | 3 |

## Capacity vs Sprint 3

| Size | Sprint 4 committed | Sprint 3 delivered |
| --- | --- | --- |
| XS | 1 | 3 |
| S | 8 | 6 |
| M | 8 | 6 |
| L | 3 | 0 |
| XL | 0 | 0 |
| Spike | 1 | 1 |

Capacity watch: Sprint 4 commits 11 items at M or larger; Sprint 3 delivered 6 that big (and zero L). The committed mix is heavier than proven throughput - confirm capacity or trim/split the larger items before locking. The two carryover L's are Business Design (owner-acknowledged); RAI-546 (Supplier Catalog) is the one to watch, as the retro flagged it blocked.

## Bugs (unsized by design)

Tracked against the Production Bugs bucket; not individually sized.

| Key | Owner | Summary |
| --- | --- | --- |
| RAI-674 | Kay | Bug – Service Providers Cannot Load Available Projects (HTTP 500 Error) |
| RAI-673 | Kay | Regression – AI Image Generation Disabled in Partner Projects |
| RAI-672 | Kay | Performance Issue – Property Images Load Slowly on Property Detail Page |

## Recommendations

- Unblock Supplier Catalog before designing it. Secure sample client catalogs first, or split RAI-546 into a research spike, rather than re-committing a blocked L.

- Stand up a per-build test suite. Retro idea; directly targets the prod regressions from hotfixes.

- Add standard user-checks across all tabs/pages. Retro idea; catches the class of bugs that leaked to prod.

- Track ad-hoc bugs against the Production Bugs bucket. The 3 late-added homeowner-registration bugs that carried over show why the reserved bucket matters.

- Right-size Sprint 4's top end. 12 items carried in; the committed mix runs heavier at M/L than proven throughput (0 L delivered two sprints running).